## Sheet1
Impact
[9 empty] | Low | Medium | High
[7 empty] | Likelihood | Low | Low | Medium | Medium
[8 empty] | Medium | Medium | Medium | High
[8 empty] | High | Medium | High | High
Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level
Bugs - Functionality/Useability | Poor optimisation of mvp functionality can end up making it run slow. Bugs can prevent the application from working completely. | Performing Backend testing; Junit, Mockito, and Front end testing; Selenium and using a statistical analysis tool like SonarQube to identify vulnerabilities and bugs within the application. | To have a fully functioning MVP ready for production. | Medium | High | High
Hardware Failure | Machine failure of personal equipment, i.e. PC/Laptop, could lead to a corruption of local files. Could also increase dwell time (unproductivity) if someone doesn't have access to a second machine. | Employ a plan B - either by having access to a second means of equipment or performing regular back-ups on the cloud. | Minimises the disruption caused by hardware failure due to regular backups. Further reduces the impact of a corrupt file and improves data integrity; the accuracy and consistency of the data stored. | Low | High | Medium
Internet Connectivity | Internet connectivity impacts the accessibility of remote files on cloud hosted websites. And prevents creating remote backups of your work. | Attending facilities offering reliable internet connection such as cafés/librararies. Changing Network providers or asking for a network engineer to resolve the issue. | Reduces the severity and inconvenience caused by the loss of internet connectivity. | Medium | Low | Medium
Github/Terminal | With the work constantly being pushing/pulling to and from the repo, entering wrong commands on the bash terminal may lead to the source code not being uploaded in its entirety. | Employ the Feature-Branch Model (FBM) to organise your work and only merging the branches to your development branch when you feel like you reached a milestone/checkpoint/a working completion of a feature. | Keeps work organised, reduces the likelihood of working codes going missing. If it does occur, can easily be reversed by looking through commit history (git log) | Low | Medium | Medium
Loss of Data | General sense; loss of data occurring from human error / accidental deletion / overwritting fully functioning codes / Hacking; Data Manipulation. | Making frequent implementation of version control to upload and track data so that it can be recovered. Using cloud hosted sites to store data such as onedrive. | Ensures minimal down time in the event of data being lost. And an easier recoverey process. | High | High | High
Power cut | Power cuts can lead to a loss of data, Can come without a warning and prevent one from accessing their pc's. It's a risk out of one's control and will need to be investigated by a third party, i.e. electricians. | Contacting the electricity provider to restore service, another way could be to have external power banks and chargers to use temporarily during downtime. | Minimises the disruptions caused and since it is a risk out of our scope, having external power can reduce downtime and allow development to continue. | Low | Medium | Medium
Illness | Can lead to a setback with the project, illness can vary between people to people. Response is not always the same. Can lead to a loss in development time on the web application. | Ensuring you take the right medications prescribed and employ a healthy eating habit. Working in a clean environment and regularly cleaning hands. | Cleaning your work surface regularly to prevent germs from being spread. | Low | Low | Low
Software Knowledge/Ability | Writing efficient and fully functioning codes is dependent on one's ability and understanding of the programming language being used. | Asking trainer for assistance when needed, scouring the net to assist with understanding. Making use of QA resources or external learning sites such as Udemy and Youtube to bridge the gap in knowledge. | To make oneself a confident developer, ensuring efficiency in one's coding. Having the mindset and ability to problem solve whether it be finding a way to make this function or resolve that error. | High | Medium | High